## Certificate #2
SUBCONTRACT INTERIM PAYMENT CERTIFICATE
Project Nr. : IFOV-TGHP-0028-03-SL029-02
Subcontractor: |  | DP Celine Fabrics Company Limited | [7 empty] | Agreement Reference : |  | IFOV-TGHP-0028-03-SL029-02
Subcontract Cert. No. : |  |  |  | 1 | [5 empty] | Month of : |  | 2023-11-13
Description of Work: |  |  |  | Supply & Installation motorized curtain
Subcontract Type: | [5 empty] | Lump Sum |  |  |  | Invoice Issued Date: |  | 2024-02-05
Contract Amount (excl. VAT): | [5 empty] | 239565580 |  |  |  | Invoice Received Date: |  | 2024-02-02
Provisional Sum (excl. VAT) | [9 empty] | Payment to be made: |  | 2024-02-17
Total Value (excl. VAT) | [5 empty] | 239565580 |  |  |  | Remaining SC Amount: |  | 27988604
PAYMENT DETAILS | [10 empty] | CUMULATIVE TO DATE | CUMULATIVE PREVIOUS |  | CURRENT MONTH
A. | WORK DONE
| A1. Value of Measured Works: | [9 empty] | 218218480 |  |  | 218218480
A2. Value of Additional Works:
A3. Value of Variation Works:
| A4. Material on Site: | [9 empty] | 0 | 0 |  | 0
| A5. Other(s): | [9 empty] | 0 | 0 |  | 0
| TOTAL VALUE OF WORK DONE | [9 empty] | 218218480 | 0 |  | 218218480
B. | LESS RETENTION | [8 empty] | 5% | 10910924 |  |  | 10910924
| SUBTOTAL (A-B) | [9 empty] | 207307556 | 0 |  | 207307556
C. | ADVANCE PAYMENT
| C1. Advance Payment | [8 empty] | 20% | 47913116 | 47913116
| C2. Recovery of Advance Payment | [8 empty] | 20% | 43643696 |  |  | 43643696
| REMAINING ADVANCE PAYMENT (C1-C2) | [9 empty] | 4269420 | 47913116 |  | 43643696
D. | ADD - VAT 8%
E | DEDUCTION (Back Charges) | [9 empty] | 0 | 0 |  | 0
| GROSS AMOUNT DUE FOR PAYMENT (A-B+C+D-E) | [9 empty] | 211576976 | 47913116 |  | 163663860
SUBCONTRACT PARTICULARS
Actual Progress (%): |  |  |  |  | 91% | [5 empty] | DP Celine Fabrics Company Limited
Currency of Payment: |  |  |  |  | VND | [5 empty] | 75/39/9 Street 48, Quarter 6
Place of Payment: |  |  |  |  | VND | [5 empty] | Hiep Binh Chanh Ward
Sub-contract signed on: | [10 empty] | Thu Duc City, HCMC, Vietnam
P-Bond Value: | [6 empty] | Valid up to: |  | N/A |  | 0
A/P-Bond Value: | [6 empty] | Valid up to: |  | N/A |  | 0
Insurance: |  |  | 0 |  |  |  | Valid up to: |  | N/A |  | 0
COMMENTS
0
REVIEW AND APPROVAL
[8 empty] | Dated |  |  | Name |  | Signature
Prepared |  |  |  | QS |  |  |  | 2024-02-05 |  |  | Gary Wan
Reviewed |  |  |  | Project Manager |  |  |  | 2024-02-05 |  |  | Gareth Wyn Owen

## Certificate#1
I.F.O. S.r.l.
SUBCONTRACT INTERIM PAYMENT CERTIFICATE
Project Nr. : IFOV-TGHP-0028-03-SL029-02
Subcontractor: |  | DP Celine Fabrics Company Limited | [7 empty] | Agreement Reference : |  | IFOV-TGHP-0028-03-SL029-02
Subcontract Cert. No. : |  |  |  | 1 | [5 empty] | Month of : |  | 2023-11-13
Description of Work: |  |  |  | Supply & Installation motorized curtain
Subcontract Type: | [5 empty] | Lump Sum |  |  |  | Invoice Issued Date: |  | 2023-11-08
Contract Amount (excl. VAT): | [5 empty] | 239565580 |  |  |  | Invoice Received Date: |  | 2023-11-13
Provisional Sum (excl. VAT) | [5 empty] | 0 |  |  |  | Payment to be made: |  | 2023-11-28
Total Value (excl. VAT) | [5 empty] | 239565580 |  |  |  | Remaining SC Amount: |  | 191652464
PAYMENT DETAILS | [10 empty] | CUMULATIVE TO DATE | CUMULATIVE PREVIOUS |  | CURRENT MONTH
A. | WORK DONE
| A1. Value of Measured Works: | [9 empty] | 0 | 0 |  | 0
| A2. Value of Additional Works: | [9 empty] | 0 | 0 |  | 0
| A3. Value of Variation Works: | [9 empty] | 0 | 0 |  | 0
| A4. Material on Site: | [9 empty] | 0 | 0 |  | 0
| A5. Other(s): | [9 empty] | 0 | 0 |  | 0
| TOTAL VALUE OF WORK DONE | [9 empty] | 0 | 0 |  | 0
B. | LESS RETENTION | [9 empty] | 0 | 0 |  | 0
| SUBTOTAL (A-B) | [9 empty] | 0 | 0 |  | 0
C. | ADVANCE PAYMENT
| C1. Advance Payment | [8 empty] | 20% | 47913116 | 0 |  | 47913116
| C2. Recovery of Advance Payment | [8 empty] | 20% | 0 | 0 |  | 0
| REMAINING ADVANCE PAYMENT (C1-C2) | [9 empty] | 47913116 | 0 |  | 47913116
D. | ADD - VAT 10% | [9 empty] | 0 | 0 |  | 0
E | DEDUCTION (Back Charges) | [9 empty] | 0 | 0 |  | 0
| GROSS AMOUNT DUE FOR PAYMENT (A-B+C+D-E) | [9 empty] | 47913116 | 0 |  | 47913116
SUBCONTRACT PARTICULARS
Actual Progress (%): |  |  |  |  | 0% | [5 empty] | DP Celine Fabrics Company Limited
Currency of Payment: |  |  |  |  | VND | [5 empty] | 75/39/9 Street 48, Quarter 6
Place of Payment: |  |  |  |  | VND | [5 empty] | Hiep Binh Chanh Ward
Sub-contract signed on: | [10 empty] | Thu Duc City, HCMC, Vietnam
P-Bond Value: | [6 empty] | Valid up to: |  | N/A |  | 0
A/P-Bond Value: | [6 empty] | Valid up to: |  | N/A |  | 0
Insurance: |  |  | 0 |  |  |  | Valid up to: |  | N/A |  | 0
COMMENTS
0
REVIEW AND APPROVAL
[8 empty] | Dated |  |  | Name |  | Signature
Prepared |  |  |  | QS |  |  |  | 2023-11-13 |  |  | Gary Wan
Reviewed |  |  |  | Project Manager |  |  |  | 2023-11-13 |  |  | Alain Heisser
Approved |  |  |  | Project Director |  |  |  | 2023-11-13 |  |  | Mario Soldi
Note on P26: G. Chararas: released on monthly basis

## MeasSheetSummary
|  |  | Subcontract Order/ Contract |  |  | Previous Application |  |  | This Application |  |  | Cumulative Application
[6 empty] | 1 |  |  | 2 |  |  | 2
No | Description | Unit | Qty | Rate | Total | Qty 1 | Rate 1 | Total 1 | Qty 2 | Rate 2 | Total 2 | Qty 2 | Rate 2 | Total 2 | Approved Qty | Approved Amount
1 | Roller blind fabrics | m
1 | CONDITION A | Set
2 | Roller blind fabrics | m2 | 6.4935 | 1530000 | 9935055 |  |  |  | 6.7896 | 1530000 | 10388088 | 6.7896 | 1530000 | 10388088 | 6.4935 | 9935055 | DP/IFO/DO-080124-01
3 | Tube & bottom bar | Lm | 1.755 | 650000 | 1140750 |  |  |  | 1.845 | 650000 | 1199250 | 1.845 | 650000 | 1199250 | 1.755 | 1140750 | DP/IFO/DO-080124-01
4 | Sonesse 40 RTS 3/30 (Motor) | Set | 1 | 9570000 | 9570000 |  |  |  | 0 | 9570000 | 0 | 0 | 9570000 | 0
5 | Sonesse 40 RTS 6/20 (Motor) | Set |  |  | 0 |  |  |  | 1 | 12000000 | 12000000 | 1 | 12000000 | 12000000 | 1 | 9570000 | DP/IFO/DO-080124-01
6 | Fabrication | m2 | 6.4935 | 280000 | 1818180 |  |  |  | 6.7896 | 280000 | 1901088 | 6.7896 | 280000 | 1901088 | 6.4935 | 1818180
7 | Internal easy link bracket | Set | 0 | 3800000 | 0 |  |  |  | 0 | 3800000 | 0 | 0 | 3800000 | 0 | 0
8 | Installation work | m2 | 6.4935 | 200000 | 1298700 |  |  |  | 6.7896 | 200000 | 1357920 | 6.7896 | 200000 | 1357920 | 6.4935 |  | For claim this item need to include WIR
2 | CONDITION B | Set | [6 empty] | 0 |  | 0 | 0 |  | 0
1 | Roller blind fabrics | m2 | 6.438 | 1530000 | 9850140 |  |  |  | 5.4096 | 1530000 | 8276688 | 5.4096 | 1530000 | 8276688 | 6.438 | 9850140 | DP/IFO/DO-080124-01
2 | Tube & bottom bar | Lm | 1.74 | 650000 | 1131000 |  |  |  | 1.47 | 650000 | 955500 | 1.47 | 650000 | 955500 | 1.47 | 955500 | DP/IFO/DO-080124-01
3 | Sonesse 40 RTS 3/30 (Motor) | Set | 1 | 9570000 | 9570000 |  |  |  | 0 | 9570000 | 0 | 0 | 9570000 | 0
4 | Sonesse 40 RTS 6/20 (Motor) | Set |  |  | 0 |  |  |  | 1 | 12000000 | 12000000 | 1 | 12000000 | 12000000 | 1 | 9570000 | DP/IFO/DO-080124-01
5 | Fabrication | m2 | 6.438 | 280000 | 1802640 |  |  |  | 5.4096 | 280000 | 1514688 | 5.4096 | 280000 | 1514688 | 6.438 | 1802640
6 | Internal easy link bracket | Set | 0 | 3800000 | 0 |  |  |  | 0 | 3800000 | 0 | 0 | 3800000 | 0
7 | Installation work | m2 | 6.438 | 200000 | 1287600 |  |  |  | 5.4096 | 200000 | 1081920 | 5.4096 | 200000 | 1081920 |  |  | For claim this item need to include WIR
3 | CONDITION C | Set | [6 empty] | 0 |  | 0 | 0 |  | 0
1 | Roller blind fabrics | m2 | 9.805 | 1530000 | 15001650 |  |  |  | 9.8992 | 1530000 | 15145776 | 9.8992 | 1530000 | 15145776 | 9.805 | 15001650 | DP/IFO/DO-080124-01
2 | Tube & bottom bar | Lm | 2.65 | 650000 | 1722500 |  |  |  | 2.69 | 650000 | 1748500 | 2.69 | 650000 | 1748500 | 2.65 | 1722500 | DP/IFO/DO-080124-01
3 | Sonesse 40 RTS 3/30 (Motor) | Set | 1 | 9570000 | 9570000 |  |  |  | 0 | 9570000 | 0 | 0 | 9570000 | 0
4 | Sonesse 40 RTS 6/20 (Motor) | Set |  |  | 0 |  |  |  | 1 | 12000000 | 12000000 | 1 | 12000000 | 12000000 | 1 | 9570000 | DP/IFO/DO-080124-01
5 | Fabrication | m2 | 9.805 | 280000 | 2745400 |  |  |  | 9.8992 | 280000 | 2771776 | 9.8992 | 280000 | 2771776 | 9.805 | 2745400
6 | Internal easy link bracket | Set | 0 | 3800000 | 0 |  |  |  | 0 | 3800000 | 0 | 0 | 3800000 | 0
7 | Installation work | m2 | 9.805 | 200000 | 1961000 |  |  |  | 9.8992 | 200000 | 1979840 | 9.8992 | 200000 | 1979840 |  |  | For claim this item need to include WIR
4 | CONDITION D | Set | [6 empty] | 0 |  | 0 | 0 |  | 0
1 | Roller blind fabrics | m2 | 24.79 | 1530000 | 37928700 |  |  |  | 24.5456 | 1530000 | 37554768 | 24.5456 | 1530000 | 37554768 | 24.79 | 37928700 | DP/IFO/DO-080124-01
2 | Tube & bottom bar | Lm | 6.7 | 650000 | 4355000 |  |  |  | 6.67 | 650000 | 4335500 | 6.67 | 650000 | 4335500 | 6.7 | 4355000 | DP/IFO/DO-080124-01
3 | Sonesse 40 RTS 3/30 (Motor) | Set | 2 | 9570000 | 19140000 |  |  |  | 0 | 9570000 | 0 | 0 | 9570000 | 0
4 | Sonesse 40 RTS 6/20 (Motor) | Set | 0 |  | 0 |  |  |  | 2 | 12000000 | 24000000 | 2 | 12000000 | 24000000 | 2 | 19140000
5 | Fabrication | m2 | 24.79 | 280000 | 6941200 |  |  |  | 24.5456 | 280000 | 6872768 | 24.5456 | 280000 | 6872768 | 24.79 | 6941200
6 | Internal easy link bracket | Set | 1 | 3800000 | 3800000 |  |  |  | 0 | 3800000 | 0 | 0 | 3800000 | 0
7 | Installation work | m2 | 24.79 | 200000 | 4958000 |  |  |  | 24.5456 | 200000 | 4909120 | 24.5456 | 200000 | 4909120 |  |  | For claim this item need to include WIR
5 | CONDITION E | Set | [6 empty] | 0 |  | 0 | 0 |  | 0
1 | Roller blind fabrics | m2 | 20.3315 | 1530000 | 31107195 |  |  |  | 20.6448 | 1530000 | 31586544 | 20.6448 | 1530000 | 31586544 | 20.3315 | 31107195 | DP/IFO/DO-080124-01
2 | Tube & bottom bar | Lm | 5.495 | 650000 | 3571750 |  |  |  | 5.61 | 650000 | 3646500 | 5.61 | 650000 | 3646500 | 5.495 | 3571750 | DP/IFO/DO-080124-01
3 | Sonesse 40 RTS 6/20 (Motor) | Set | 1 | 12000000 | 12000000 |  |  |  | 2 | 12000000 | 24000000 | 2 | 12000000 | 24000000 | 1 | 12000000 | DP/IFO/DO-080124-01
4 | Fabrication | m2 | 20.3315 | 280000 | 5692820 |  |  |  | 20.6448 | 280000 | 5780544 | 20.6448 | 280000 | 5780544 | 20.3315 | 5692820
5 | Internal easy link bracket | Set | 1 | 3800000 | 3800000 |  |  |  | 0 | 3800000 | 0 | 0 | 3800000 | 0
6 | Installation work | m2 | 20.3315 | 200000 | 4066300 |  |  |  | 20.6448 | 200000 | 4128960 | 20.6448 | 200000 | 4128960 |  |  | For claim this item need to include WIR
II | Other accessories | [7 empty] | 0 |  | 0 | 0 |  | 0
| Remote Stuo 5 RTS | Set | 1 | 3800000 | 3800000 |  |  |  | 1 | 3800000 | 3800000 | 1 | 3800000 | 3800000 | 1 | 3800000 | DP/IFO/DO-080124-01
III | Survey and delivery fee | Package | 1 |  | 20000000 |  |  |  | 1 | 20000000 | 20000000 | 1 | 20000000 | 20000000 |  | 20000000
| Total |  |  |  | 239565580 |  |  | 0 |  |  | 254935738 |  |  | 254935738 |  | 218218480
| SUBMITTED AND AGREED BY | [7 empty] | APPROVED BY
| NAME OF SUBCON/SUPPLY | [7 empty] | ITALIANFITOUT COMPANY LIMITED

## Certificate Input
SUBCONTRACT PAYMENT CERTIFICATE | [5 empty] | Project: | [5 empty] | Subcontractor
[10 empty] | Order Value | 239565580
|  |  | Cumulatives for Cert No. 2 | Cumulative S/C Application | Measured Works | Additional Works | Variation Works | Materials on Site | Others | AP Amount | 47913116 | Current Value | Retention | Current less Retention | Cumulatives for Cert No. 2 | Reversal of Advance Payment | Reversal of Retention | Contra Charges
|  |  | Current App. | 0 | 218218480 | 0 | 0 | 0 |  |  |  | 0 | 10910924 | 207307556 | Current App. | 4269420 | 0 | 0
|  |  | Previous App. | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | Previous App. | 47913116 | 0 | 0
|  |  | Movement | 0 | 218218480 | 0 | 0 | 0 |  |  |  | 0 | 10910924 | 207307556 | Movement | -43643696 | 0 | 0
[10 empty] | AP Recovery | 20%
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Certificate No. | Date Inv. Submitted | Date Inv. Received | Month End | Cumulative S/C Application | Measured Works | Additional Works | Variation Works | Materials on Site | Others | Retention % | COMMENTS (Invoice numbers etc) | Current Value | Retention | Current less Retention | Cumulative | Reversal of Advance Payment | Reversal of Retention | Contra Charges | Contra Charges Comments
1 | <=Input a starting Payment Certificate number if required.
1 | 2023-11-08 | 2023-11-13 | 2023-11-13 | [12 empty] | 47913116
2 | 2024-02-02 | 2024-02-02 | 2024-01-01 |  | 218218480 |  |  |  |  | 5% |  | 218218480 | 10910924 | 207307556 |  | -43643696
Formulas:
Date Inv. Submitted = '[1]Certificate Input'!$B13
Date Inv. Received = '[1]Certificate Input'!$C13
Month End = '[1]Certificate Input'!$D13

## Order Details
Subcontract Order Details
| Project Name | Grand Hang Bai
Project No.
Trade
Subcontract Order
| Order No. | IFOV-TGHP-0028-03-SL029-02
| Issue Date | 31/10/2023
| Signed Date | 31/10/2023
| Type of Contract | Lump Sum
| Currency | VND
| Original Value | 239565580
SA01
SA02
SA03
SA04
SA05
SA06
SA07
Revised Value
Certified Variations
| Advance Payment (Original) | 47913116
Advance Payment (SA01)
Advance Payment (SA02)
Advance Payment (SA03)
Advance Payment (SA04)
Advance Payment (SA05)
Advance Payment (SA06)
Advance Payment (SA07)
| AP Recovery | 20%
| Retention | 5%
Retention Limit
Material on Site
Place of Payment:
Payment Days after Invoice
P-Bond Value
Date Expires
A/P-Bond Value
Date Expires
Insurance
Date Expires
Subcontractor
Name
Address
Contact Number
Signatories
QS
Project Manager

## Breakdown qty (hidden)
SUMMARY OF VOLUME OF WORK COMPLETED BY CONTRACT BẢNG TỔNG HỢP KHỐI LƯỢNG CÔNG VIỆC HOÀN THÀNH THEO HỢP ĐỒNG
TP.HCM, 26/12/2023
Package: | FILL INFORMATION HERE
Project name: | CONSTRUCTION OF INTERIOR DESIGN (ID) FIT-OUT FOR THE GRAND HANOI PROJECT AT 22-24 HANG BAI AND 25+27 HAI BA TRUNG STREETS, HANG BAI AND TRANG TIEN WARDS, HOAN KIEM DISTRICT, HA NOI, VIET NAM
Contract number: | FILL INFORMATION HERE
Subcontractor/ Supply: | FILL INFORMATION HERE
No/ STT | Item Description/ Hạng mục công việc | đơn vị tính (Unit) | AMOUNT/ KHỐI LƯỢNG |  |  |  | Remark
|  |  | LONG/DÀI | WIDE/ RỘNG | TỔNG/ TOTAL | TỔNG/ TOTAL
|  |  | m | m |  | m2
I | Roller blind fabrics
1 | Delivery note No DP/IFO/DO-080124-01 date 25/01/2024 | [5 empty] | Confirmed by…., Material approve No 093 & 094.
1 | CONDITION A | Set
2 | Roller blind fabrics | m2 | 1.845 | 3.68 | 6.7896
3 | Tube & bottom bar | Lm |  |  | 1.845
4 | Sonesse 40 RTS 3/30 (Motor) | Set |  |  | 0
5 | Sonesse 40 RTS 6/20 (Motor) | Set |  |  | 1
6 | Fabrication | m2 |  |  | 6.7896
7 | Internal easy link bracket | Set |  |  | 0
8 | Installation work | m2 |  |  | 6.7896
2 | CONDITION B | Set
1 | Roller blind fabrics | m2 | 1.47 | 3.68 | 5.4096
2 | Tube & bottom bar | Lm |  |  | 1.47
3 | Sonesse 40 RTS 3/30 (Motor) | Set |  |  | 0
4 | Sonesse 40 RTS 6/20 (Motor) | Set |  |  | 1
5 | Fabrication | m2 |  |  | 5.4096
6 | Internal easy link bracket | Set |  |  | 0
7 | Installation work | m2 |  |  | 5.4096
3 | CONDITION C | Set
1 | Roller blind fabrics | m2 | 2.69 | 3.68 | 9.8992
2 | Tube & bottom bar | Lm |  |  | 2.69
3 | Sonesse 40 RTS 3/30 (Motor) | Set |  |  | 0
4 | Sonesse 40 RTS 6/20 (Motor) | Set |  |  | 1
5 | Fabrication | m2 |  |  | 9.8992
6 | Internal easy link bracket | Set |  |  | 0
7 | Installation work | m2 |  |  | 9.8992
4 | CONDITION D | Set
1 | Roller blind fabrics | m2 | 6.67 | 3.68 | 24.5456
2 | Tube & bottom bar | Lm |  |  | 6.67
3 | Sonesse 40 RTS 3/30 (Motor) | Set |  |  | 0
4 | Sonesse 40 RTS 6/20 (Motor) | Set |  |  | 2
5 | Fabrication | m2 |  |  | 24.5456
6 | Internal easy link bracket | Set |  |  | 0
7 | Installation work | m2 |  |  | 24.5456
5 | CONDITION E | Set
1 | Roller blind fabrics | m2 | 5.61 | 3.68 | 20.6448
2 | Tube & bottom bar | Lm |  |  | 5.61
3 | Sonesse 40 RTS 6/20 (Motor) | Set |  |  | 2
4 | Fabrication | m2 |  |  | 20.6448
5 | Internal easy link bracket | Set |  |  | 0
6 | Installation work | m2 |  |  | 20.6448
II | Other accessories |  |  |  | 0
| Remote Stuo 5 RTS | Set |  |  | 1
III | Survey and delivery fee | Package |  |  | 1
Signed for and on behalf of the Purchaser Signed for and on behalf of the Vendor Ký cho và thay mặt Bên Mua Ký cho và thay mặt Bên Bán