## EIT Maping (hidden)
2.1 ERI | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
ERI-Register & search -> done in 2021
Order - ENG/CIS -> done in 2021
Order PO control: ETA, return, export PO -> done in 2021
Order link data new, re-issue PO | Jan: 45%
Order link data adjust, cancel PO | Jan: 50%
Order Adjust PO | Jan: 60%
Assembly design interface | Feb: 65%
Coding Assembly-Responsible Dept | Feb: 70%; Mar: 80%
Testing Assembly Responsible Dept | Mar: 90%
Fix errors | Mar: 100%
Improve: show data by right of user, PO link NPIS | Apr: 100%
Improve: Order Inhouse, part need export / not for LOG | May: 100%
2.2 TVP | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Coding TVP Home: create, confirm, check, approve for PE/PQA/PDC1 | Jan: 20%
Coding TVP Home- Revise, return, up version | Jan: 25%
Design Part/Unit Production | Jan: 40%
Code Part/Unit Production | Feb: 50%; Mar: 60%; Apr: pending
Test Part/Unit Production | 100% May: 70%
Coding PO | 100% Jun: 85%
Coding return function, check all condition prevent wrong data | 100% Jun: 90%
Test all system | 100% Jun: 100%
Launching System
2.3 TID | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Study Concept | Jan: 10%
Design interface | Feb: 20%
Design DB | Feb: 30%
Coding Issue problem | Mar: 40%; Apr: 50%
Coding Respond countermeasure | May: 60%
Coding Confirm countermeasure | May: 70%
Coding Apply countermeasure | May: 80%
Testing | May: 90%
Fix code | Jun: 100%
Launching
2.4 ECS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Design DB, Interface | May: 20%
Coding Issue dept | May: 50%
Coding PQA dept | Jun: 80%
Test | Jun: 100%
IV. DMS2-Calculation Die | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Study flow & Concept | 100% Jun: 10%
Design interface | 100% Jul: 20%
Coding | 100% Jul: 60%
Testing | 100% Aug: 80%
Meeting to review | 100% Aug: 90%
Fix code | 100% Sep: 100%
V.DMS3-Die Trouble | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Study Concept | 100% Oct: 10%
Design interface | 100% Oct: 20%
Coding | 100% Oct: 40%; 100% Nov: 70%
Testing | 100% Nov: 90%
Fix code | 100% Dec: 100%
VI.Eng Portal Site - challenge | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Study Concept | Oct: 10%
Design Interface | Oct: 20%
Coding | Oct: 40%; Nov: 70%
Testing | Nov: 90%
Fix code | 100% Dec: 100%
VII. New Model Launching | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Study flow | Oct: 10%
Design Interface & DB | Oct: 20%
Coding | Oct: 40%; Nov: 70%
Test | Nov: 90%
Fix Code | 100% Dec: 100%

## ERI (hidden)
EIT Coding Item master map
2.1 ERI
Done
Doing
Plan
Delay
1 |  | 2 | 3 | 4 | 6
Main menu | Target | No | Status | Function | Remark
Register & Search | 20% | 1 |  | Register Control ERI No for New/Upversion
|  | 2 |  | Delete ERI
|  | 3 |  | Search
|  | 4 |  | Download format/data
|  | 5 |  | Link from ERINo to menu ENG/CIS
|  | 6 |  | Upload Master list Supplier for PUR
Order - Responsible Dept | 15% | 1 |  | Confirm charging/ return PE
ENG/CIS | 25% | 1 |  | Issue ERI
|  | 2 |  | Revise after issue
|  | 3 |  | Check ERI
|  | 4 |  | Approve ERI
|  | 5 |  | Return ERI
|  | 6 |  | Search
|  | 7 |  | Divide and add right for dept to open file direct on server
PO Control | 50% | 1 |  | PUR confirm/check/approve ETA
|  | 2 |  | PUR return Buyer/ return PE
|  | 3 |  | PUR update ETA, attachment for multi item
|  | 4 |  | PUR cancel order
|  | 5 |  | Search/ download
|  | 6 |  | PDC1/CIS PDC/PPD confirm/check/approve pre PO
|  | 7 |  | Export PO in format csv
|  | 8 |  | Return PUR
|  | 9 |  | PO issued to confirm which item issued
|  | 10 |  | Adjust PO
|  | 11 |  | approve adjust PO
|  | 12 |  | Link NPIS new, re-issue po
|  | 13 |  | Link NPIS for cancel, adjust PO
PO History | 60% | 1 |  | Show all history
|  | 2 |  | search & download
|  | 3 |  | update procedure
Assembly - Responsible Dept | 10% | 1 |  | PE issue/check/approve/return | same form with order but different interface
|  | 2 |  | Upversion, cancel
|  | 3 |  | PQA & Responsible check & Fill data to cover | 1. PQA not input Estimate date, Responsible need input 2. PQA & Responsible need input other information(Yes/No) => Need change ERI table in DB (This info is confirming by manager)
| 20% | 4 |  | PQA & Responsible approve & Fill data to cover
|  | 5 |  | PQA & Responsible return to PE Issuer | Checker & Approver alway return PE Issuer hay là Approver => Checker => PE Issuer
|  | 6 |  | Update Estimate date before PE verify | Trước khi PE verify , vì distribute không còn là pdf, cũng kp fill vào file
|  | 7 |  | Verify check
|  | 8 |  | Verify approve
|  | 9 |  | Make Master ERI file export
|  | 10 |  | Test PQA & Responsible
|  | 11 |  | Test Fill data to cover
|  | 12 |  | Test Return
|  | 13 |  | Test Verify
Improve System |  |  |  | ERI order for Inhouse
ERI type export for LOG form

## TVP (hidden)
EIT Coding Item master map
2.2 TVP
Done
Doing
Plan
Delay
1 |  | 2 | 3 | 4 | 5 | 6
Coding TVP Home | Target | No | Status | Function |  | Remark
Coding TVP Home | 25% | 1 |  | Register
|  | 2 |  | Delete TVP
|  | 3 |  | Search
|  | 4 |  | Stop TVP
|  | 5 |  | Upversion
|  | 6 |  | PE confirm/check/approve
|  | 7 |  | PDC confirm route
|  | 8 |  | PQA implement confirm/check/approve
|  | 9 |  | Return
Design part Unit | 40% | 1 |  | Design gridview follow request PDC2/PQA
|  | 2 |  | Highlight color by status
|  | 3 |  | Gridview scroll
|  | 4 |  | Interface for each dept input qty, date in popup
Code Part/Unit Production | 60% | 1 |  | Show all data in grid view
|  | 2 |  | Page index
|  | 3 |  | Input for Plan Delivery(out)/ production(in)
|  | 4 |  | Input for Manufacturing dept produce
|  | 5 |  | Input for PDC2 received outside
|  | 6 |  | Input for MQA(Outsoure Part/Unit)
|  | 7 |  | Double data if check NG
|  | 8 |  | Input for PDC2 input store
|  | 9 |  | Input for PDC2 supply next process
|  | 10 |  | Input for Manufacturing receiver
|  | 11 |  | Input for TVP result (OK qty)
|  | 12 |  | Input for PDC2 transfer NPIS
|  | 13 |  | input for PDC1 close TVP
|  | 14 |  | input for PDC1 close TVP
|  | 15 |  | Search/download
Test Home - Part/Unit Production | 70% | 1 |  | Test function PE
|  | 2 |  | Test PDC, PQA
|  | 3 |  | Test return in Home
|  | 4 |  | Show all data in grid view
|  | 5 |  | Page index
|  | 6 |  | Input for Plan Delivery(out)/ production(in)
|  | 7 |  | Input for Manufacturing dept produce
|  | 8 |  | Input for PDC2 received outside
|  | 9 |  | Input for MQA(Outsoure Part/Unit)
|  | 10 |  | Double data if check NG
|  | 11 |  | Input for PDC2 input store
|  | 12 |  | Input for PDC2 supply next process
|  | 13 |  | Input for Manufacturing receiver
|  | 14 |  | Input for TVP result (OK qty)
|  | 15 |  | Input for PDC2 transfer NPIS
|  | 16 |  | input for PDC1 close TVP
|  | 17 |  | input for PDC1 close TVP
|  | 18 |  | Search/download
Coding PO | 0% | 1 |  | Apply code ERI PO to TVP
Test all system again | 100% | 1 |  | check email, wrong data, prevent mistake

## PIR (hidden)
EIT Coding Item master map
2.3 PIR
Done
Doing
Plan
Delay
1 |  | 2 | 3 | 4 | 5 | 6
Coding TVP Home | Target | No | Status | Function |  | Remark
Study Concept | 20% | 1 |  | Checking flow from document
|  | 2 |  | Meeting with SID group
Design interface | 25% | 1 |  | Menu Home ( only 1 menu) |  | Not yet have detail concept, wait Nguyet san confirm
Coding | 80% | 1 |  | Create PIR
|  | 2 |  | Delete
|  | 3 |  | Issue/approve for Issue Dept
|  | 4 |  | Confirm/check/approvecountermeasure
|  | 5 |  | Confirm/approve apply countermeasure
|  | 6 |  | Upversion
|  | 7 |  | Return from inside and outside 1 dept
|  | 8 |  | Issue/check/approve in Responsible dept
|  | 9 |  | Revise/ Return in Responsible
Testing | 80% | 1 |  | Create PIR
|  | 2 |  | Delete
|  | 3 |  | Issue/approve for Issue Dept
|  | 4 |  | Confirm/check/approvecountermeasure
|  | 5 |  | Confirm/approve apply countermeasure
|  | 6 |  | Upversion
|  | 7 |  | Return from inside and outside 1 dept
|  | 8 |  | Issue/check/approve in Responsible dept
|  | 9 |  | Revise/ Return in Responsible
Meeting to review | 90% | 1 |  | All function
Fix code | 100% | 1 |  | All function
Chi dien vao Remark why delay nhe

## ECS (hidden)
EIT Coding Item master map
2.3 PIR
Done
Doing
Plan
Delay
1 |  | 2 | 3 | 4 | 5 | 6
Coding TVP Home | Target | No | Status | Function |  | Remark
Design DB, Interface | 20% | 1
2
3
Coding | 80% | 1
2
3
4
8
9
Test | 100% | 1
2
3
4
8
9
NY get idea

## DMS (hidden)
EIT Coding Item master map
2.3 DMS
Done
Doing
Plan
Delay
1 |  | 2 | 3 | 4 | 5 | 6
Coding TVP Home | Target | No | Status | Function |  | Remark
Design DB, Interface | 20% | 1
2
3
Coding | 80% | 1
2
3
4
8
9
Test | 100% | 1
2
3
4
8
9
NY get idea

## RPA (hidden)
EIT Coding Item master map
2.3 PIR
Done
Doing
Plan
Delay
1 |  | 2 | 3 | 4 | 5 | 6
Coding TVP Home | Target | No | Status | Function |  | Remark
DSUM upload | 100% | 1 |  | Explain concept for Kien san -Huong
|  | 2 |  | Get data DSUM need send Yako by SQL
Adv group code RPA
ECN download | 100% | 1 |  | Explain concept for Kien san -Huong
|  | 2 |  | Get data ECN need download by SQL
Adv group code RPA
ECAR Upload | 100% | 1 |  | Explain concept for Kien san -Huong
|  | 2 |  | Get data ECAR need send Yako by SQL
Adv group code RPA
Ai se explain?
Sao lai delay
Ai se explain?
Sao lai delay

## ADV action plan
[68 empty] | #VALUE! |  |  | CPL-0001
Attachment 1/ Rev. 02
Department : |  | TIM | [5 empty] | Departmental annual action plan: | [36 empty] | Plan |  |  |  |  | NG result | [8 empty] | Issue |  |  |  |  | Review (Mgr) |  |  |  | Approve (Mgr)
Cost Center : |  | 613 | [6 empty] | .Is issued by head of department no later than 1 month since top policy is released. | [49 empty] | Hoang Manh Truong | [8 empty] | Le Thi Duyen
Division : |  | TL ENG DIV | [6 empty] | .Aims at (is linked) to Departmental policy & objectives, upper level policies. | [35 empty] | Good result |  |  |  |  | Apply
Control No : |  | Plan-2023 | [6 empty] | .Is reviewed as nessessary, in compliance with company situation. | [35 empty] | * Updating might be by overwriting or inserting
Ver01 | [8 empty] | .Annual review is required, to company top management, detailed content is attached as necessary. | [35 empty] | lines below the lines of plan
[8 empty] | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 |  |  |  | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01
|  |  | Operation Themes |  | Target | PIC | Result | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
ADV group
Theme | Job |  |  | Break Job
Visual Inspection Check (2023~2024) | Concept study |  |  | Study mold part (Specific criteria are for passing or failing the inspection)
Decide priority part
| Jig, Accessary,equipment investigation |  |  | Study which jig/accessary using (cameras, sensors, or other types of visual inspection tools, that will be used to capture the required data)
Jig layout (transfer system, Camera, Lighting system)
Camera-Lighting direction adjust
| A6. Human cultivation |  |  | ER issue q'ty | 16 items |  |  | 2023-03-01 w1: Truong; 2023-04-01 w1: Huong; 2023-05-01 w1: V/Anh; 2023-06-01 w1: Hai; 2023-07-01 w1: Tu; 2023-08-01 w1: Truong; 2023-09-01 w1: V/Anh; 2023-10-01 w1: Hai; 2023-11-01 w1: Tu
[24 empty] | Hiep |  |  |  | Kien |  |  |  | Ngoc |  |  |  | Huong |  |  |  | Hiep |  |  |  | Kien |  |  |  | Ngoc
Quick ER issue 1 person/week/1 set (G3~G5) | bar: 2023-01-01 w4; 2023-02-01 w4
| Inspection Software study |  |  | Camera connection programing module
Take Image module
Preprocess data module ( Clean and normalize the dataset. This includes resizing images, removing noise, and augmenting the dataset with techniques like rotation, flipping, and zooming)
Establish inspection procedures (Study Machine learning/AI model)
Data collection (Need to collect a large amount of data to train AI model)
Traning the model
Fine-tune the model (improve its accuracy)
Test the model
Deploy the model
Program interface
| Adaptation to the production line |  |  | Real-layout in Mold work shop
Get again data Image
Review gain Traning model
Fine-tune the model (improve its accuracy)
Judment the model
Deploy the project

## ADV mapping (hidden)
A1- Master key | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | FEB | Done | Plan | Delay
1. Design cover box | Jan: 10% | Masterkey | 90% | 10% | 0%
2. Request making (MTP) | Jan: 10% | Mini projector | 30% | 70% | 0%
3. Box assembly | Feb: 10%; Mar: 10% | Abnormal sound | 80% | 20% | 0%
4. Study electric componet (Pi, Python, sensor, relay, lock) | Jan: 10% | Rosetta | 40% | 60% | 0%
5. Study connection | Jan: 10% | Checker data visualize | 20% | 80% | 0%
6. Repair connection | Jan: 10% | Apply RPA/OCR for Job | 25% | 75% | 0%
7. Promote API for better flow | Jan: 10%
8. Verify API connection (API, network…) | Jan: 10%
9. Lay out election componet to box | Feb: 10%; Apr: 10%
10. Promote function for display status on 7'' LCD | Feb: 10%; Mar: 10%
A2- Mini projector | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Study concept | Jan: 10%
2. Study current electic componnent | Jan: 10%
3. Study method remote to Tablet screen (GM request) | 10% Feb: 10%
4. Order necessary electric component (HDMI ⇔ USB type C) | 10% Apr: 10%
5. Coding (Python code) | 10% Apr: 10%
6. Design cover (by NX) | 10% Mar: 10%
7. Making cover (By 3D printer) | 10% Apr: 10%
8. Assembly | 10% May: 10%
9. Verify | 10% May: 10%
10. 1st lauch product | 10% May: 10%
A3- Abnormal sound | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Receive & study concept | bar: Jan
2. How to commnuicate Checker program (C#) to Sound Inspect (Python) study | Jan: 10%
3. Meeting LBP Shinmaruko side | bar: Jan
4. Request send demo tool for commnication testing | bar: Jan
5. Program test tool (test commnucate) | Jan: 10%
6. Setting Python enviroment variable | Jan: 10%
7. Making steplist to connect to KMK steplist | Feb: 10%
8. Joint to seqence of printer by CFP (togther MFE1 support) | Feb: 10%
9. PC preparation (Ram, HVDD, …) | bar: Jan
10. Software setting (Request IT & Shinmaruko member) | Jan: 10%
11. Verification by actual printer | bar: Feb
12. Follow ultil apply to cells | bar: Mar
13. Study Sound inspection (Python code) | bar: 10% Jul
14. Follow Sound Inspec and Advanced | bar: 10% Dec
B1- Rosetta/GP4 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Start Study concept Rosetta | Jan: 10%
2.Meeting for sharing T.T doc from Yako member | Jan: 10%
3. Self study with 22A (Houston/Edea) Tria | Feb: 20%
4. Actual investigation 23A model( From DC phase) | 5% Dec: 100%
5. Follow 23A from MP
6. 24A start official use
B2- Checker data visualize | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Follow push 22A PSU data (FCT/Hipod final) to server | Mar: 20%
Follow push 22A VE checker to server | Apr: 20%
Coding (Trace/ Visualize data/Checker link) | May: 80%
Debug/Verify | Jun: 90%
Introduction and get FB | Jun: 100%
Apply
B3- Apply RPA/OCR for Job | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
2. OCR study equiupment | Mar: 10%
3. OCR study project for asset inventory | Apr: 20%
4. Order equipment | Jun: 30%
5. PC connection/ commnunication with OCR eqiupment study | Jun: 50%
6. Sofwave coding (By Pthon) | Aug: 80%
5.Verify and testing | Sep: 90%
6. Meeting to TIM PIC to explaination and one more time verify | Sep: 100%
7. Apply and finish project

## EIT- PIC (hidden)
E_IT_2022 Action Plan
[8 empty] | Plan-Huong |  | Plan-Huyen |  | Plan-V.Anh |  | New comer
No | JOB | DETAIL ACTIONS |  |  |  | TARGET | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | EIT group | 1.1. Maintain & upgrade system
|  |  | 1.1.1. VE - Visualize |  |  | 100%
1.1.3. DMS step 1 - PO FOC
|  |  | 1.1.4. DMS step 1 - PUC |  |  | 100%
1.1.5. DMS step 1 - link Discard
1.2. Document Control
1.2.1. ERI
|  |  |  | PO-ERI order |  | 100%
Design Assembly
Coding Assembly
Testing
|  |  | 1.2.2. TVP |  |  | 100%
Coding TVP Home
Test TVP Home
Design Part/Unit Production
Code Part/Unit Prodcution
Test Part/Unit Production
Code PO
Test PO
Lauching System
1.2.3. PIR - Problem invest request
Design interface
Coding
Testing
Launching
|  |  | 1.2.4.ECS |  |  | 100%
Design
Coding
Testing & Apply
1.3. RPA - Kien
DSUM upload
ECN download
ECAR upload
1.4. Die Management System step 2 - Calculation Die
|  |  |  | Study Concept & Fomula |  | 100%
Meeting & fix concept
Design DB & Interface
Coding
Standard Data in DMS
Testing & Maintain
|  | 1.5. Die Management System Step 3 - Die Trouble |  |  |  | challenge
Design Interface
Design DB
Coding
Testing
1.6. Eng Portal Site
|  |  |  | Meeting & Design Concept |  | challenge
Collect data, content for system
Code DB and interface
|  | 1.7. New Model launching |  |  |  | challenge
Study procedure
Meeting & design concept
Coding
Testing
2 | HUMAN CULTIVATION
1.1. Training for other
1.2. Engineering Report (4 ER)

## EIT Detail (2) (hidden)
EIT Coding Item maping
Done
Doing
Plan
Delay
None
|  |  | <sample 1> |  |  |  | <sample 2>
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
|  |  | 10 | Coding TVP Home |  | 5 | 12 | Coding TVP Home |  | 5
|  |  | 9 | 8 | 7 | 6 | 11 |  |  | 6
[7 empty] | 10 | 9 | 8 | 7
2.2 TVP
Coding TVP Home |  |  |  | No | Content
|  |  |  | 1 | Item 1
1 | 2 | 3 | 4 | 2 | Item 2
10 | Coding TVP Home |  | 5 | 3 | Item 3
9 | 8 | 7 | 6 | 4 | Item 4
Finish: | 10% |  |  | 5 | Item 5
Status: | 4.444% |  |  | 6 | Item 6
|  |  |  | 7 | Item 7
|  |  |  | 8 | Item 8
|  |  |  | 9 | Item 9
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.